## Sheet1
APACHE MEETING MINUTES
Title | Cutting Material Management Meeting Review | Date / Time | 2025/07/31 ( 09 : 30 - 11 : 00 ( IST ) )
Place | GM Office | Attendants | derek-yang , Chandrasekhar , syamsundar , manohar , manoj kumar , lucas Sir , Rossi-Chou
Meeting Content
Topic | Discussed | Remarks / Follow up
Cutting Material Management Report | Average Cutting Line Stoppage & Future Goal To Be Implemented In Production | 1. Starts the tracking with planning team 2 . Co ordinate with other departments for how to do their job
| The Prototype For Cutting Material Management | 1. How to visualize system with accuracy 2. need to Visualize Some UI
| Tracking Real Time Production and SAP Data & Suggestions To Departments | 1. From the next week need to add Rossia for the every Thursday meeting 2. Need to visualize the report in sigle page 3. Need to Develop single page or 3 click step page.
Next Week Plans
1. Identify and remove unused materials in the BOM, or categorize them separately for better management. 2. Retrieve July data and August planning data for the AP5 E Plant (C25) from the Planning Department. Analyze July’s performance to support accurate and improved planning for August. 3. List and review all issues identified in the schedule data to ensure proactive resolution.