## Sheet1
APACHE MEETING MINUTES
Title | Cutting Material Management Weekly Meeting Review | Date / Time | 2025/08/21 ( 09 : 30 - 10 : 30 ( IST ) )
Place | Original Meeting Room | Attendants | derek-yang , manohar , manoj kumar
Meeting Content
Topic | Discussed | Remarks / Follow up
Cutting Material Management Report | Discussed About Line wise blue print and real time development | Understand the process flow and give earlier indicators to the Production through web development
| Draw backs in Present Planning process | Needs to develop an web application for plannig reschedule and schedule
| Suggestions to resolve to draw backs | Add Material Name column in web development
Next Week Plans
1. Needs to confirm with Planning team about Requirement for planning reschedule function 2. Develop an web application for planning reschedule function 3. Get SAP Data to Database through FMS.