## Sheet1
APACHE MEETING MINUTES
Title | END TO END Analysis Weekly Meeting Review | Date / Time | 2025/06/26 ( 09 : 30 - 11 : 00 ( IST ) )
Place | War Meeting Room | Attendants | derek-yang , Chandrasekhar , syamsundar , manohar , manoj kumar
Meeting Content
Topic | Discussed | Remarks / Follow up
Pull BOM | 1 . Done by BOM Team 2 . ZMM123 T-code is used to pull BOM Data | 1 . BOM Must be clear , No need to add extra material in BOM 2. Need to discuss with bom team about bom data
Placing Purchase Orders | 1 . How to Buy Material? 2 . How to Fetching the fetching sheet? | 1 . Track ASN T-code
Fetching Generation | 1 . How to generate fetching sheet 2 . Checking required quantity and applied quantity in fetching system | 1 . Need to check status for a picking number in fetching system should be clear
Material Availability For Cutting | 1 . Checking material for each stage C / S / L / A . | 1 . How to identify material is for cutting . 2 . Should be clarify that how many materials are for a PO
Planning | _ | 1 . Planning should be contain accurate dates and live accurate data.
Next Week Plans
1 . Track the all Earlier discussions and Create a prototype for cutting material Availability Project .