## Sheet1
APACHE MEETING MINUTES
Title | END TO END Analysis Weekly Meeting Review | Date / Time | 2025/07/03 ( 09 : 30 - 11 : 00 ( IST ) )
Place | War Meeting Room | Attendants | derek-yang , Chandrasekhar , syamsundar , manohar
Meeting Content
Topic | Discussed | Remarks / Follow up
Prototype | 1. Clarified the purpose and responsibilities of the Planning team 2. Plan to prepare materials at least 7 days in advance of scheduled cutting/production. 3. Clarified the purpose and responsibilities of the Planning team 4. Reviewed the current flow and suggested changes for better integration between departments. 5. Explore integration to fetch material availability against BOM automatically. | 1. Need to coordinate with APE for accurate ASN (Advanced Shipping Notice) visibility. 2. Prepare detailed reports PO-wise, Line-wise, Plant-wise for better overview. 3. Enhance Organization flow for cutting material management.
Purchase System | 1. Discussed how POs impact material readiness. 2. Discuss about cost modification in purchase material. 3 . Discussed about fetching system. | 1. How cost is updated or modified in SAP. 2. Clarified who has authority to modify cost; suggestion to restrict access only to designated supervisors. 3. What is the use of ZMM023 and what is the purpose. 4. Need for proactive PO monitoring and ASN tracking.
Next Week Plans
Enhance prototype for second version and Prepare for Monday’s session focusing on tracing SAP data flow from order to warehouse for one specific PO.