## Sheet1
APACHE MEETING MINUTES
Title | Cutting Material Management Weekly Meeting Review | Date / Time | 2025/07/10 ( 09 : 30 - 11 : 00 ( IST ) )
Place | IT Office Meeting Room | Attendants | derek-yang , Chandrasekhar , syamsundar , manohar
Meeting Content
Topic | Discussed | Remarks / Follow up
Cutting Material Management Report | Tracked material readiness (BOM, Purchase, Warehouse, and material fetching) for a specific Sales Order (SO). | Provide actual data for one line's material readiness.
| Verified real-time data accuracy in SAP. | Update PPT slides to include Production Planning and Warehouse Finished Goods.
| Reviewed the prototype of the final report. | Finalize and confirm the latest version of the BOM
| Discussed SAP-to-report data connectivity. | Ensure planning dates are accurate and consistent.
| Verified issued vs. unissued quantity in the report. | Needs to prepare Final Version Report.
Next Week Plans
Focus on tracking material readiness for a selected production line.