## Sheet1
APACHE MEETING MINUTES
Title | END TO END Analysis Weekly Meeting Review | Date / Time | 2025/06/19 ( 09 : 30 - 11 : 00 ( IST ) )
Place | War Meeting Room | Attendants | derek-yang , Chandrasekhar , syamsundar , manohar
Meeting Content
Topic | Discussed | Remarks / Follow up
Sales order Creation | 1 . Done by Order Team 2 . VA01 T-code is used for manually upload one sales order data 3 . ZSD001N T-Code is used for bulk upload 4 . VA02 T-Code is used for modification of Saled oder data | 1 . Need to clarify the use and purpose of VA01 T-code
Pull BOM | 1 . Done by BOM Team 2 . ZMM123 T-code is used to upload BOM Data | 1 . Upper part is ok for BOM 2 . As Bottom no of chemical parts have issue 3 . BOM Must be clear , No need to add extra material in BOM
Create Collection | 1 . APE Team create the collection through ZMM018 and ZMM019 T-codes | 1 .Need to confirm with APE Team how they create collection and run
Placing Purchase Orders | 1 . Done by Purchase Team 2 . Purchase orders placed through ZMM020 T-Code | 1 . Need to check with warehouse department about stock quantity 2 . Avaid to purchase over quantity 3 . Must be clear with BOM Team
Material Receive | 1 . The mateial was received through WMS Platform | 1 . Campare material availability in WMS with SAP
Planning schedule | 1 . Done by Planning Team through ZPP003 T-Code | 1 . Get clarify for all the date in ZPP003 T-Code
Fetching Generation | 1 . Done by ERP Team through ZPP005 T-Code | 1 . Need to know the process flow of ERP Team 2 . If Loss the paper whats the futher process 3 . If warehouse has no stock why the fetching sheet
Next Week Plans
1 . Discuss Topics related to Fetching, Production, FG Inbound, and Shipment 2 . Follow up on all the follow ups 3. Focus on improving Sales Order Creation and BOM Pull process