## Sheet1
项目计划 Project Plan
序号 No | 项目名称 Item | 任务 Task | 负责人 PIC | 开始日期 Start Date | 结束日期 End Date | 天数 Days
1 | Initiating | Project Plan
Confirm Project Team
Plan Explanation/Review Meeting
2 | Execution | 1.Data Capture and Integration |  | 01-07-2025 | 2025-07-15 | 13
|  | 1.1) focusing on tracing SAP data flow from order to warehouse for one specific PO. |  | 2025-07-01 | 2025-07-01
|  | 1.2 ) Enhance Prototype. |  | 2025-07-04 | 2025-07-06
|  | 1.3) Pull ASN (Advanced Shipping Notice) from APE |  | 2025-07-07 | 2025-07-08
|  | 1.4) Auto-sync SAP BOM and PO Data |  | 2025-07-09 | 2025-07-11
|  | 1.5) Real-time warehouse stock update |  | 2025-07-12 | 2025-07-15
|  | 2. Validation & Exception Management |  | 16-07-2025 | 2025-08-04 | 17
|  | 2.1) BOM vs Material Availability Validation ( Highlight shortages, mismatches ) |  | 16-07-2025 | 19-07-2025
|  | 2.2) GRN Delay Flagging ( Alert when material is not GRN’d before deadline ) |  | 20-07-2025 | 24-07-2025
|  | 2.3) Cost Mismatch Alerting ( Validate cost data before material readiness ) |  | 25-07-2025 | 29-07-2025
|  | 2.4) Escalation Trigger Rules ( Auto/manual escalation logic setup ) |  | 30-07-2025 | 2025-08-04
|  | 3. User Role-based Dashboards |  | 05-08-2025 | 2025-08-25 | 18
|  | 3.1) GM Dashboard ( Plant-wise readiness %, escalation trends, delay summary ) |  | 05-08-2025 | 2025-08-10
|  | 3.2) Plant Incharge Dashboard ( PO status by line, shortage tracking, team escalations ) |  | 10-08-2026 | 2025-08-15
|  | 3.3) Line Supervisor View ( PO readiness, issued vs pending, material request panel ) |  | 15-08-2027 | 2025-08-20
|  | 3.4 ) Cross-Dept View ( Shared material view for Planning, Purchase, Warehouse ) |  | 20-08-2028 | 2025-08-25
|  | 4. Reports & Alerts |  | 25-08-2025 | 2025-09-10 | 14
|  | 4.1) Critical Material Shortage Report ( Based on quantity, delays, escalation frequency ) |  | 25-08-2025 | 2025-08-30
|  | 4.2) Escalation Report by Dept ( Shows unresolved issues by department ) |  | 31-08-2026 | 2025-09-03
|  | 4.3) Downloadable PO-Wise Report ( For audit/tracking purposes ) |  | 04-09-2027 | 2025-09-06
|  | 4.4) Daily Material Readiness Mailer ( Auto-send summary to warehouse ) |  | 07-09-2028 | 2025-09-10
|  | 5. Notifications and Communication |  | 11-09-2025 | 19-09-2025 | 8
|  | 5.1) In-App Notifications ( Role-based notification alerts ) |  | 2025-09-11 | 2025-09-13
|  | 5.2) Email Alerts ( For escalations, PO delays, etc. ) |  | 2025-09-14 | 2025-09-16
|  | 5.3) WhatsApp Integration (optional) ( Quick alerts to ground-level teams ) |  | 2025-09-17 | 2025-09-19
|  | 6. User Access and Audit Control |  | 20-09-2025 | 25-09-2025 | 5
|  | 6.1) Supervisor-Level Authority Restrictions ( Only allow certain edits or confirmations ) |  | 2025-09-20 | 2025-09-25
|  | 7. Material Forecasting & Planning Insights |  | 26-09-2025 | 03-10-2025 | 7
|  | 7.1) Suggest Material Need for Next 7 Days ¦ Based on schedule ¦ |  | 2025-09-26 | 2025-09-28
|  | 7.2) Highlight Blocking Materials per Line ¦ Auto-calculate delays caused ¦ |  | 2025-09-29 | 2025-10-01
|  | 7.3) Compare Issued vs BOM QTY ¦ Help planning adjust based on availability ¦ |  | 2025-10-02 | 2025-10-03
|  | 8. Feedback & Continuous Improvement |  | 04-10-2025 | 18-10-2025 | 13
|  | 8.1) Collect Dept-Wise Feedback ( From Line Supervisor, Planning, WH, etc. ) |  | 2025-10-04 | 2025-10-10
|  | 8.2) Weekly Review Meeting ( Review escalations, delays, improvement areas ) |  | 2025-10-11 | 2025-10-14
|  | 8.3) Suggest Improvements / System Updates ( Regular system tuning ) |  | 2025-10-15 | 2025-10-18
3 | Acceptance | SOP Documentation for Usage |  | 20-10-2025 | 22-10-2025 | 3
|  | Finalization of Escalation & Reporting Flow |  | 23-10-2025 | 25-10-2025 | 3
4 | Closure | Final Review and Project Summary ¦ |  | 27-10-2025 | 31-10-2025 | 5