## Slide 1
APACHE APC MES
Cutting Material Management
System
Presented by : Manohar-G ( APC-IT )
2025 September 24
Apache Footwear India Private Limited
Report Presented

## Slide 2
🛠 Meeting Focus Areas
项目沟通 Project Communication
6
项目沟通-工具 Project Communication- Tools
5
4
项目组织 Project Organization
2
项目规划 Project Schedule
1
项目范围 Project Scope
3
项目团队Project Team
项目规划 Project Schedule
项目范围 Project Scope
项目团队Project Team
项目组织 Project Organization
项目规划 Project Schedule
项目范围 Project Scope
项目团队Project Team

## Slide 3
项目范围 Project Scope
序号 No. | 类别 Category | 范围内 Scope-in | 范围外 Scope-out | 备注 Remark
1 | 系统系统System | 1. The Cutting Material Management System aims to enhance material tracking and availability across production lines. The system will enable monitoring of material status for each PO , helping to proactively identify and address potential shortages. By predicting material unstock situations, the solution will reduce line stoppages and improve overall production efficiency. Additionally, the system will be integrated with MES to trigger automatic email alerts for rescheduling, ensuring timely communication and smoother operational flow. | - | 
2 | 平台 Platform | MES (customized function) | MES | 
3 | 区域 Region | APC | - | 

## Slide 4
项目规划 Project Schedule
Close
完成
Delay
延迟
On-going
进行中
Not start
未开始
We are here
2026/01/10 Go-live
Not Started
09/19 PI
2026/01/10 Go-live
PI
09/19 Delay
12/27 User training
Not started
蓝图Blueprint
09/24 Ongoing
09/24 KO & Blueprint Review
2026/01/08 Project sign-off
KO Prep
09/24 Ongoing
09/24 Kick-off
09/09
09/12
01/30
09/15
09/18
09/20
01/04
GRR：2026/01/08
Not started
01/10
Project Exit：2026/02/17
Not started
Realization ：2025/12/27 Not started
12/20
12/20
12/27
02/17
01/08

## Slide 5
Project Team
Project Team
Project Manager
Manohar-G
Supporting Team
IT
Project Development Team
Planning
Purchase
Manohar-G
Derek-yang
Chandrasekhar-v
Nagarjuna
Balaji-v
Warehouse
Rakhi
Syamsundar-r

## Slide 6
项目组织 Project Organization
Project Sponsors
Project Group Management Office (PMO)
Project Director: Chandra (IT)
Project Manager-APC: Manohar-g (IT)
Core Business Process Group
Planning Department
BPO : Nagarjuna,
KU : Rakhi
BPO: business process owner
APC IT
Team Leader : Syamsundar-r
Project Developers : Manohar-g
Steering Committee
Rakhi , Derek-yang , Balaji-v ,
Manohar-g
Purchase Department
Warehouse Department
BPO : Derek-yang
KU : Derek-yang
BPO : Balaji-v
KU : Balaji-v
IT

## Slide 7
项目沟通 Project Communication
Type of Communication | Frequency | Purpose and Content | Output | Originator | Attendees / Senders
Weekly Report | Every Saturday till project go-live APC 16:00-16:30 | Email report on project progress | Project Progress Report | IT | IT Members
Weekly meeting – Project | Every Thursday till project go-live | Report on the progress of the project Next work plan Where help is needed | Meeting Minutes | IT | Planning , Warehouse , Purchase , IT , Production
Email
WhatsApp
项目沟通-工具 Project Communication- Tools

## Slide 8
CMT 工作流程 CMT Work-flow
Data Capture
Top
Management
Production
Cutting Material Report
Purchase Team
Warehouse Team
BOM
Planning Team
Plant In-charge
Line Supervisor
Top Management
Issue materials, verify stock
Track Purchase Status
View overall readiness %
material trends
Sees high-level overview
Check assigned POs start cutting only if fully ready escalate
Track PO-wise readiness
material issues
escalate to teams
Ensure BOM is accurate
validate material need
resolve errors
Provides base material requirements.
Input purchase data
Warehouse stock data
Cutting Material Report auto-syncs BOM,PURCHASE, WAREHOUSE, PLANNING AND PO DATA| Triggers alerts and tracks material readiness
Assigns
shares

## Slide 9
📋 Assigned Pos
5
✅ Ready to Cutting
3
❌ Not Ready
1
⚠ Escalated
1
Day | Line | PO NO | Article | Material Status
2025/07/05 | AP11CO5 | 1000042525 | Samba | ✅ OK
 |  | 1000042579 | Samba | ❌ Short
PO NO | Article | Material | Material Name | Required Qty | Available Qty | Shortage Qty | Status | Invoice | ETA
1000206709 | Samba | M001 | Material 1 | 125 | 125 | 0 | ✅ OK |  | 
1000206709 | Samba | M002 | Material 2 | 520 | 300 | 220 | ❌ Short | INV-MAT-20240620-0048 | 2025/07/05
1000042579
PO NO
By default the field takes short material status po in ascending order
1000042579
PO NO
Enter Issue
Issue
Submit
1000042579
PO NO
Check
PO Readiness List
Material Checklist by PO
Raise Escalations
Request store verification
All
PO NO
All
Status
All
Line
Check
Check
Cutting Material Availability – Line Supervisor
📆
From
📆
TO
2025/07/01
2025/07/05

## Slide 10
📋 Total POs Today
28
✅ Fully Ready Pos
19
🚫 Shortage Pos
7
🔁 Delayed Pos
2
Date | PO NO | Model | Plant | Line | Material Readiness % | Status | Delay | Action
2025/07/02 | 1000042579 | SAMBA | AP11 | AP11C02 | 100% | ✅ Ready | - | Start Cutting
 | 1000042525 | STANSMITH | AP10 | AP10C04 | 75% | ❌ Short | 1 DAY | Escalate
 | 1000215486 | ULTIMATE | AP09 | AP09CO3 | 90% | ❌ Short |  | 
2025/07/03 | 1000042578 | SAMBA | AP11 | AP11C02 | 100% | ✅ Ready | - | Start Cutting
 | 1000042524 | STANSMITH | AP10 | AP10C04 | 100% | ✅ Ready | 1 DAY | Escalate
 | 1000215485 | ULTIMATE | AP09 | AP09CO3 | 90% | ❌ Short |  | 
Material Name | Required Qty | Available Qty | Short Qty
Fabric A | 200m | 160m | 40m
Check
PO-Wise Material Readiness Status
All
Plant
All
Line
All
PO NO
All
Status
Cutting Material Availability – Plant In-charge Dashboard
📆
From
📆
TO
2025/07/01
2025/07/05

## Slide 11
📦 Material Readiness %
82% Ready
🚨 Open Escalations (issues not yet resolved)
5
📋 Total POs Today
36
📈 Avg Delay
2.1 days
Chart: Material Readiness by Plant
| Plant -B | Plant -C | Plant -D | Plant - E | Plant - F | Plant - G | Plant - H | Plant - I | Plant - J | Plant - K
Series 1 | 0.7 | 0.6 | 0.45 | 0.8 | 0.56 | 0.68 | 0.98 | 0.75 | 0.65 | 1
Material | Short Quantity | Affected Pos
FTWR WHITE 01F7 54 | 340m | 3
1.4MM ECO SOFT MATTE | 220m | 8
CEMENT TWICE | 165m | 21
WHITE LATEX | 100m | 4
ST-A990-06E EPM5 MESH | 92m | 1
Top 5 Short Materials :
All
Plant
All
Line
Submit
Purpose: Compare different plants to see which ones are better prepared for cutting.
Description : Shows % of material availability across all assigned POs
Benefits : Identify which plant is performing well and where attention or escalation is needed.
Purpose: Highlight the most frequently short or unavailable materials, across all POs.
Benefits : Quickly identify which raw materials are causing the biggest disruptions—helps guide procurement priorities
Cutting Material Availability Dashboard – Top Management
📆
From
📆
TO
2025/07/01
2025/07/03
Date | No Of Pos | Material OK Pos | Material Not OK Pos | Material Readiness % | Status
2025/07/01 | 120 | 120 | 0 | 100% | ✅ Ready
2025/07/02 | 154 | 150 | 4 | 97% | ❌ Short
2025/07/02 | 182 | 140 | 42 | 75% | ❌ Short