## 模板 Template
万邦 IT 项目立项申请书 APACHE IT Project Initiation Application Form | [5 empty] | 填写说明 Instructions | Instructions-English
项目名称 Project name | Cutting Material Management System |  |  | 项目编号 Project number | MES25008 | 》所有栏位都只接受中文或英文或中英文双语填写； 》涉及非中文区域时，建议使用英文填写。 》《IT 分析说明 IT Analysis》之前的内容由业务主导填写；其中：项目编号 Project number, 最后一步 PMO 填写合规性时填写； | 》All fields can only be filled in Chinese or English or "both Chinese and English"; When non-Chinese areas are involved, it is recommended to fill in English. The content before "IT Analysis" is filled by the business PM; The project number will be filled in when the PMO fills in the compliance at the last step.
申请人 Applicant | Manohar-G | 申请部门 Application dept | IT | 涉及区域 Related Region | APC | 涉及区域（可填写多项）：APE,APC,APH,HK,SG,TW | Related Region (multiple items can be filled in)：APE,APC,APH,HK,SG,TW
项目类型 Project Type | 部门级战略项目 Dept level strategic project |  |  |  |  | 》项目类型判断：如在公司级战略项目清单（例如列在HK项目中）或部门战略清单中，选择对应的项目类型； 如不在相关清单中或无法判断是否为战略项目（例如，战略项目尚未确定），选择“其他 Others”。 》项目类型，影响项目优先级。 》如当地尚无战略项目清单，新建工厂类（独立法人）项目默认公司级战略项目。 | 》Project type judgment: select the corresponding project type if the project is in the company-level strategic project list (for example, listed in the HK project) or departmental strategy list; If it is not in the relevant list or if it is unsure whether it is a strategic project (for example, the strategic project has not been identified), select "Others". 》Project type affects project priority. 》If there is no list of strategic projects in the local area, a new plant implementation (independent legal person) projects will be a company-level strategic project by default.
期望上线时间 Expected launch time | 2025-12-31 |  |  |  |  | 不确定具体上线日期的情况下，颗粒度到月份即可； | If not sure about the specific launch date, month is acceptable;
项目需求 Project Req. | 1. The Real time System preperation for planing schdeule and reschdule data and Day wise targets 2. Real time cutting material status monotoring and reduce line stoppage in plants.
项目效益 Project benefits | "The Cutting Material Management System project aims to streamline production by providing real-time visualization of material status across all cutting lines. By tracking the status of each purchase order (PO), the system helps reduce cutting line stoppages and improves operational efficiency. It also enables better production planning and scheduling by eliminating manual Excel-based processes, ensuring faster and more accurate decision-making." Soft Saving : Gaining 0.5 spike score Hard Saving : Can Saves 0.5 Hours Per Working Day For Each Person in Plant and 1 hour Per Working Day for each person in Planning team Total Mds Saved: 4095 Mds (50 Staff *0.5 HourPer Day *26 Working Days Per Month*12 Months*3 Years/8 HoursPerDay) + ( 10 staff * 1 hourper Day * 26 Working Days Per Month* 12 Months * 3 Years / 8 HoursPerDay) Hard Saving-Amount: 37723.94 USD |  |  |  |  | 收入，按照3年进行估算。 | Income is estimated based on 3 years. | 352.4
业务投入人天 Biz MDs | Bussines Team invest approximately 40.125 man Days |  |  | 折算金额 Amount for biz MDs | BIZ: 369.64 USD | 如涉及部门较多，请另外附各部门投入人数 & 人天。 用户人天主要用于需求沟通、参与例会、参与培训、测试、数据整理、提供最终用户培训、参与上线切换任务等； | Users are in charge of demand communication, regular meetings, training, testing, data collation, providing end-user training, online switching tasks, etc.
业务项目经理 Business PM | Nagarjuna-Y | 签字确认 Sign-off
IT 分析说明 IT Analysis | [5 empty] | IT 分析说明 IT Analysis：由IT进行填写。 | IT Analysis: Filled in by IT.
影响系统 Relevant systems | MES
IT可行性分析 IT Feasibility Analysis | Easy Analysis And Tracking Of PO Data Through Graphical Representation.
IT投入人天 IT MDs | 项目投入Project input：95.975 运维投入Maintanence input：35 |  |  | 折算金额 Amount for IT MDs | 1206.57 USD | 应包含项目投入+3年的IT运维投入； 跨区域项目，应包含各区域IT投入。 注意：运维投入仅用于计算ROI，不影响项目的投入大小。 不要遗漏配合单位，例如，数据部。 不含日常运维支持的部门，例如，为了做项目，需要给部分用户开网络权限，算作IT日常运维工作，无需算作项目投入。 3年的运维投入是指运维该项目（例如，处理bug、解疑答惑；不含新增运维需求处理）的IT投入。 | Invest: project investment + 3 years of IT maintenance investment; For cross-region project, input should include the IT input from the relevant regions. Note: maintenance investment is only used to calculate ROI （Return on investment）, and does not affect the project's investment size. Please include the support team, for example, basis. For departments that offer daily operation and maintenance support, are not included. For example, in order to carry out projects, some users need to get network permissions, which is counted as IT daily operation and maintenance work, and does not need to be counted as project investment. Maintenance investment: for example, handling bugs, answering questions; excluding new requirements processing.
其他投入金额 Other input | NA |  |  | 其他投入承担部门 Responsible dept for other input | NA | 》其他投入金额：包含但不限于硬件投入、软件购买成本、外部顾问成本、推广等； 如IT无足够人力支持，需要外包人力进行开发，属于“其他投入”。 》其他投入承担部门，需负责对应的预算和付款申请、追踪事项。 | 》Other investment amount: including but not limited to hardware investment, software cost, external consultant fee, promotion fee, etc.; If IT does not have sufficient manpower support and need outsourcing manpower, it belongs to "other inputs". 》Other investment undertaking departments are responsible for the corresponding budget, payment application, and tracking tasks.
总投入 Total input | 1576.21 USD |  |  | 投资回报率 ROI | 2393% | 投资回报率=收入/成本*100% 项目管理方法论运行初期，不对ROI 做硬性要求，ROI小的项目，优先级较低。 未来规划：ROI ＜1 的项目，原则上不予实施。 | Return on investment = revenue / cost * 100% In the early stage of project management, there is no requirement on ROI. Projects with small ROI are with lower priority. Future plan: Projects with ROI <1 will not be implemented.
IT项目经理 IT PM | Manohar-G | 签字确认 Sign-off
相关业务部门主管签核确认 Sign-off from relevant business dept leaders
区域 Region | 部门 Dept | 部门主管 Dept Leader | 指派的项目代表 Assigned focal | 签核确认及签核意见 Sign-off and comments
APC | Planning | Nagarjuna-Y | Rakhi
APC | Production Control | Siva-C
APC | Purchase | Derek Yang
APC | Warehouse | Ramesh-K | Balaji-V
IT签核确认 Sign-off from IT
区域 Region | 部门 Dept | 部门主管 Dept Leader | 指派的项目代表 Assigned focal | 签核确认及签核意见 Sign-off and comments
APC | IT | Chandrasekhar-V
APC | IT- MES | Syamsundar-r | Manohar-G
总经理签核确认 Sign-off from GM
签核确认 Sign-off |  |  | 签核意见 Sign-off comments
合规性检查确认 Compliance Check and Confirmation | [5 empty] | 合规性检查确认：由PMO进行填写。 | Compliance Check and Confirmation：filled in by PMO.
检查确认 Data check |  | 签字确认 Sign-off after check |  | 签字日期 Sign-off date |  | 》签字日期为立项完成日期； | Sign-off date: project initiation application complete date.