## Sheet1
Region | Category | Test ID test ID | scene description | Requirements | Plan start | Plan finish | Actual start | Actual finish | Owner | Status | Remark
APC | Decision Making | SIT_01 | 1 . Getting Knowledge From Visual Dashboards of Production 2. Cutting stopage Lines Identification 3. Automatic Escalations Understanding and Immediate Response | need to check all data About Planning Schedule Data and Warehouse material status data and Identify Cutting stoppage lines and Sending Escalation to Each Department and Checks Raw material Issues | 2025-12-17 | 2025-12-18 | 2025-12-22 | 2025-12-24 | Manohar-G | Close