## End To End
序号 No. | 类别 Category | 检核项 Check list | 责任人 Owner | 目标完成 Target date | 实际完成 Actual finish | 状态 Status | 备注Remark
1 | 蓝图BP | 业务解决方案签核确认Business solution sign-off |  |  |  | Close
2 | 蓝图BP | IT解决方案签核确IT solution sign-off |  |  |  | Close
3 | 培训Training | 关键用户都已经参加培训All key users attend training |  |  |  | Close
4 | 培训Training | 最终用户都已经参加培训All end users attend training |  |  |  | Close
5 | 培训Training | 最终用户通过培训检验 All end users pass training test/exam |  |  |  | Close
6 | 培训Training | 已经制作系统操作手册和相关的管理制度 SOPs and related management files have been output |  |  |  | Not applicable
7 | 测试Test | 已经进行SIT测试，测试结果满足上线需求 SIT pass and fulfill go-live requirements |  |  |  | Close
8 | 测试Test | 已经进行了UAT测试，测试结果满足上线需求 UAT pass and fulfill go-live requirements |  |  |  | Close
9 | 测试Test | 已进行压力测试，测试结果满足上线需求 Performance test pass and fulfill go-live requirements |  |  |  | Close
10 | 测试Test | 已进行回归测试，测试结果满足上线需求 Regression test pass and fulfill go-live requirements |  |  |  | Close
11 | 测试Test | 已进行用户权限测试，测试结果满足上线需求 Rights test pass and fulfill go-live requirements |  |  |  | Close
12 | 上线前准备 Final Prep. | 上线切换策略已经输出并达成共识 MTP strategy output and aligned |  |  |  | Not applicable
13 | 上线前准备 Final Prep. | 上线切换承诺书签署确认 Move-to-production Commitment file sign-off |  |  |  | Not applicable
14 | 上线前准备 Final Prep. | 上线切换任务规划输出 Move to production planoutput |  |  |  | Not applicable
15 | 上线前准备 Final Prep. | 网络正常，服务器和客户端的软件已经安装并测试可以正常使用 Network is OK, the server and client software have been installed and tested and can be used normally |  |  |  | Close
16 | 上线前准备 Final Prep. | 相关用户的账号权限在正式系统都已经建立完毕 The accounts and rights of relevant users have been established. |  |  |  | Close
17 | 上线前准备 Final Prep. | 基础数据准备完毕，并已经录入正式环境，且由用户确认准确 Master data has been prepared and entered into the production database, and confirmed by the user. |  |  |  | Close
18 | 上线前准备 Final Prep. | 已经明确上线之后的问题反馈和解决流程（PPS Plan） The problem feedback and fixing process after the go-live has been clarified (PPS Plan) |  |  |  | Close
19 | 上线前准备 Final Prep. | 各阶段主要项目输出文档均已记录并上传 The documents of each phase have been recorded and uploaded |  |  |  | Close
Project Readiness Summary: Ready for go-live