## Slide 1: APACHE APC MES Cutting Material Management System
e万行动，e-Apache, one Apache

## Slide 2: 目录 Content
2
项目规划 Project Schedule
1
项目范围 Project Scope
3
项目团队Project Team
5
项目沟通-工具 Project Communication- Tools
6
项目沟通 Project Communication
4
项目组织 Project Organization

## Slide 3: 项目范围 Project Scope
序号 No. | 类别 Category | 范围内 Scope-in | 范围外 Scope-out | 备注 Remark
1 | 系统系统System | 1. The Cutting Material Management System aims to enhance material tracking and availability across production lines. The system will enable monitoring of material status for each PO , helping to proactively identify and address potential shortages. By predicting material unstock situations, the solution will reduce line stoppages and improve overall production efficiency. Additionally, the system will be integrated with MES to trigger automatic email alerts for rescheduling, ensuring timely communication and smoother operational flow. | - | 
2 | 平台 Platform | MES (customized function) | MES | 
3 | 区域 Region | APC | - | 

## Slide 4: 项目规划 Project Schedule
Close
完成
Delay
延迟
On-going
进行中
Not start
未开始
We are here
2026/01/10 Go-live
Not Started
01/15 PI
2026/01/10 Go-live
PI
09/15 Delay
12/27 User training
Not started
蓝图Blueprint
09/20 Ongoing
02/05 KO & Blueprint Review
2026/01/08 Project sign-off
KO Prep
09/18 Ongoing
09/18 Kick-off
09/09
09/12
01/30
09/15
09/18
09/20
01/04
GRR：2026/01/08
Not started
01/10
Project Exit：2026/02/17
Not started
Realization ：2025/12/27 Not started
12/20
12/20
12/27
02/17
01/08

## Slide 5
Project Team
Project Manager
Manohar-G
Supporting Team
IT
Project Development Team
Planning
Purchase
Manohar-G
Derek-yang
Chandrasekhar-v
Nagarjuna
Balaji-v
Warehouse
Rakhi
Syamsundar-r

## Slide 6: 项目组织 Project Organization
IT
Project Sponsors
Project Group Management Office (PMO)
Project Director: Chandra (IT)
Project Manager-APC: Manohar-g (IT)
Core Business Process Group
Planning Department
BPO : Nagarjuna,
KU(1) : Rakhi
BPO: business process owner
APC IT
Team Leader : Syamsundar-r
Project Developers : Manohar-g
Steering Committee
Rakhi , Derek-yang , Balaji-v ,
Manohar-g
Purchase Department
Warehouse Department
BPO : Derek-yang
KU(2) : Derek-yang
BPO : Balaji-v
KU(1) : Balaji-v

## Slide 7: 项目沟通 Project Communication
Type of Communication | Frequency | Purpose and Content | Output | Originator | Attendees / Senders
Weekly Report | Every Friday till project go-live APC 16:00-16:30 | Email report on project progress | Project Progress Report | IT | IT Members
Weekly meeting – Project | Every Thursday till project go-live | Report on the progress of the project Next work plan Where help is needed | Meeting Minutes | IT | Planning , Warehouse , Purchase , IT
Email
WhatsApp
项目沟通-工具 Project Communication- Tools

## Slide 8: Thanks 態度決定高度 Attitude is altitude