## Sheet1
序号 No | 阶段 Phase | 工作事项 Item | 具体内容 Detailed content | 负责人 Owner | 参与人 Participants | 预计开始 日期 Plan Start | 预计完成 日期 Due day | 实际完成 日期 Finish data | 状态 Status | 涉及部门 Related department | 涉及人数 Related qty | 投入说明 Input description | 投入人天 Input MDs | 备注 Remark
1 | 准备 Preparation | 高阶需求调研 High-level demands study | 沟通梳理高阶需求 Communicate and output high-level requirements | Manohar-G | Manohar-G , Chandra , Syam | 2025-09-08 | 2025-09-16 |  | NOT STARTED | IT | 3 | Around 1 hours per day | 3
[5 empty] | Rokhi , Naga |  |  |  |  | Planning | 2 | Around 1 hours per day | 2 |  | Total Business Mandays
[5 empty] | Siva |  |  |  |  | PC | 1 | Around 1 hours per day | 1 |  | 40.125
[5 empty] | balaji-v |  |  |  |  | Warehouse | 1 | Around 1 hours per day | 1
[5 empty] | Derek |  |  |  |  | Purchase | 1 | Around 1 hours per day | 1
[10 empty] | Total | 8 | Around 1 hours per day | 8
2 | 准备 Preparation | 项目立项 Project initiation | 项目立项-资料填写 Project initiation-data fill in | Manohar-G | Manohar-G | 2025-09-09 | 2025-09-11 |  | NOT STARTED | IT | 1 | Around 4 hours per day | 1
3 | 准备 Preparation | 项目启动 Kick-off | Project Kick Off meeting hosted for all reated departments | Manohar-G | Manohar-G , Chandra , Syam | 2025-09-17 | 2025-09-18 |  | NOT STARTED | IT | 3 | Around 1 hours per day | 0.75
[5 empty] | Naga , Rokhi |  |  |  |  | Planning | 2 | Around 1 hours per day | 0.5
[5 empty] | Siva |  |  |  |  | PC | 1 | Around 1 hours per day | 0.25
[5 empty] | balaji-v |  |  |  |  | Warehouse | 1 | Around 1 hours per day | 0.25
[5 empty] | Derek |  |  |  |  | Purchase | 1 | Around 1 hours per day | 0.25
[10 empty] | Total | 8 | Around 1 hours per day | 2
4 | 蓝图 Blueprint | 业务蓝图设计 Business blueprint design & IT总规划输出 IT Master Plan | Based on the business(FG,Business) blueprint, design IT solutions. | Manohar | Manohar-G , Chandra , Syam | 2025-09-19 | 2025-09-19 |  | NOT STARTED | IT | 3 | Around 1 hours per day | 0.375
[5 empty] | Naga , Rokhi |  |  |  |  | Planning | 2 | Around 1 hours per day | 0.25
[5 empty] | Siva |  |  |  |  | PC | 1 | Around 1 hours per day | 0.125
[5 empty] | balaji-v |  |  |  |  | Warehouse | 1 | Around 1 hours per day | 0.125
[5 empty] | Derek |  |  |  |  | Purchase | 1 | Around 1 hours per day | 0.125
[10 empty] | Total | 8 | Around 1 hours per day | 1
5 | 蓝图 Blueprint | 蓝图汇报 Blueprint review | 针对蓝图设计成果进行汇报，确认蓝图设计方案 Report and finalize blueprint solution | Manohar-G | Manohar-G , Chandra , Syam | 2025-09-19 | 2025-09-20 |  | NOT STARTED | IT | 3 | Around 1 hours per day | 0.75
[5 empty] | Naga , Rokhi |  |  |  |  | Planning | 2 | Around 1 hours per day | 0.5
[5 empty] | Siva |  |  |  |  | PC | 1 | Around 1 hours per day | 0.25
[5 empty] | balaji-v |  |  |  |  | Warehouse | 1 | Around 1 hours per day | 0.25
[5 empty] | Derek |  |  |  |  | Purchase | 1 | Around 1 hours per day | 0.25
[10 empty] | Total | 8 | Around 1 hours per day | 2
6 | 蓝图 Blueprint | IT功能清单输出 IT FunctionList Output |  | Manohar-G | Manohar-G | 2025-09-22 | 2025-09-23 |  | NOT STARTED | IT | 1 | Around 8 hours per day | 2
7 | 实现 Realization | 功能说明书输出 Function specification output | Output IT function specification | Manohar-G | Manohar-G | 2025-09-24 | 2025-09-25 |  | NOT STARTED | IT | 1 | Around 8 hours per day | 2
8 | 实现 Realization | 功能开发 Function development |  | Manohar-G | Manohar-G | 2025-10-01 | 2025-11-29 |  | NOT STARTED | IT | 1 | Around 4 hours per day | 30
9 | 实现 Realization | 单元测试-IT Unit test-IT |  | Manohar-G | Manohar-G | 2025-10-10 | 2025-12-10 |  | NOT STARTED | IT | 1 | Around 1.3 hours per day | 11
10 | 实现 Realization | 单元测试-业务 Unit test-Biz |  | Manohar-G | Naga | 2025-10-11 | 2025-12-11 |  | NOT STARTED | Planning | 1 | Around 1 hours per day | 8
11 | 实现 Realization | 关键用户培训 Key user training |  | Manohar-G | Manohar -g | 2025-12-12 | 2025-12-16 |  | NOT STARTED | IT | 1 | Around 3 hours per day | 1.5
[5 empty] | Rokhi , Naga |  |  |  |  | Planning | 2 | Around 3 hours per day | 3
[10 empty] | Total | 3 | Around 3 hours per day | 4.5
12 | 实现 Realization | 集成测试 System integration test |  | Manohar-G | Manohar-G | 2025-12-17 | 2025-12-18 |  | NOT STARTED | IT | 1 | Around 8 hours per day | 4
13 | 实现 Realization | 用户接受测试 User acceptance test |  | Manohar-G | Manohar-G | 2025-12-19 | 2025-12-27 |  | NOT STARTED | IT | 1 | Around 3 hours per day | 3
[5 empty] | Rokhi |  |  |  |  | Planning | 1 | Around 3 hours per day | 3
[10 empty] | Total | 2 | Around 3 hours per day | 6
14 | 蓝图到上线前准备 Blueprint to Final Prep. | 主数据准备 Master data preparation |  | Manohar-g | Manohar-g | 2025-09-08 | 2025-11-29 |  | NOT STARTED | IT | 1 | Around 0.5 hours per day | 5
15 | 上线前准备 Final Preparation | 压力测试 Pressure test |  | Manohar-g | Manohar-g | 2025-12-28 | 2025-12-29 |  | NOT STARTED | IT | 1 | Around 8 hours per day | 2
16 | 上线前准备 Final Preparation | 回归测试 Regression test |  | Manohar-g | Manohar-g | 2025-12-30 | 2025-12-31 |  | NOT STARTED | IT | 1 | Around 8 hours per day | 2
17 | 上线前准备 Final Preparation | 权限设计 Rights design |  | Manohar-g | Manohar-g | 2026-01-01 | 2026-01-02 |  | NOT STARTED | IT | 1 | Around 8 hours per day | 2
18 | 上线前准备 Final Preparation | 权限测试 Rights test |  | Manohar-g | Nagarjuna | 2026-01-03 | 2026-01-05 |  | NOT STARTED | IT | 1 | Around 8 hours per day | 2
19 | 上线前准备 Final Preparation | 权限分配 Rights assignment |  | Manohar-g | Manohar-g , Naga | 2026-01-06 | 2026-01-07 |  | NOT STARTED | IT | 2 | Around 8 hours per day | 4
20 | 上线前准备 Final Preparation | 上线准备情况汇报 Go-live Readiness Review |  | Manohar-G | Manohar-G, syam, Chandra | 2026-01-08 | 2026-01-08 |  | NOT STARTED | IT | 3 | Around 4 hours per day | 1.5
[5 empty] | Naga |  |  |  |  | Planning | 1 | Around 4 hours per day | 0.5
[10 empty] | Total | 4 | Around 4 hours per day | 2
21 | 上线前准备 Final Preparation | 上线切换 Move To Production |  | Manohar-G | Manohar-G | 2026-01-09 | 2026-01-09 |  | NOT STARTED | IT | 1 | Around 4 hours per day | 0.5
[5 empty] | Naga |  |  |  |  | Planning | 1 | Around 4 hours per day | 0.5
[10 empty] | Total | 2 | Around 4 hours per day | 1
22 | 上线后支持 Post-production Support | 上线 Go-live |  | Manohar-G | Manohar-G , Naga | 2026-01-10 | 2026-01-10 |  | NOT STARTED | IT | 2 | Around 2 hours per day | 0.5
23 | 上线后支持 Post-production Support | 使用情况追踪 System utilization tracking |  | Manohar-G | Manohar-G , Syam | 2026-01-12 | 2026-02-15 |  | NOT STARTED | IT | 2 | Around 2 hours per day | 2
[5 empty] | Rokhi , Naga |  |  |  |  | Planning | 2 | Around 2 hours per day | 2
[10 empty] | Total | 4 | Around 2 hours per day | 4
24 | 上线后支持 Post-production Support | 上线后问题追踪处理 PPS issues tracking and handling |  | Manohar-G | Manohar-G , Syam | 2026-01-12 | 2026-02-15 |  | NOT STARTED | IT | 2 | Around 2 hours per day | 15
[5 empty] | Rokhi , Naga |  |  |  |  | Planning | 2 | Around 2 hours per day | 15
[10 empty] | Total | 4 | Around 2 hours per day | 30
25 | 上线后支持 Post-production Support | 项目退出 Project exit |  | Manohar-G | Manohar-G | 2026-02-17 | 2026-02-17 |  | NOT STARTED | IT | 1 | Around 1 hours per day | 0.1
[12 empty] | Total | 135.1